## Sheet1
ProjectName | ProjectDescription | StartDate | EndDate | DueDate | ProjectStatus | Milestones | MilestoneStatus
Account Center | A web-based application allowing customers to manage accounts, get information and perform other tasks related to NYPA services and products. | 2020-12-15 | 2023-06-30 | 2020-12-19 | Project-In-progress | Release to RNY Customers | Completed
Account Center | A web-based application allowing customers to manage accounts, get information and perform other tasks related to NYPA services and products. | 2020-12-15 | 2023-06-30 | 2020-12-19 | Project-In-progress | Release to WNY Customers | Completed
Account Center | A web-based application allowing customers to manage accounts, get information and perform other tasks related to NYPA services and products. | 2020-12-15 | 2023-06-30 | 2020-12-19 | Project-In-progress | Release to RNY Customers | Completed
Account Center | A web-based application allowing customers to manage accounts, get information and perform other tasks related to NYPA services and products. | 2020-12-15 | 2023-06-30 | 2020-12-19 | Project-In-progress | Release to WNY Customers | Completed
Account Center | A web-based application allowing customers to manage accounts, get information and perform other tasks related to NYPA services and products. | 2020-12-15 | 2023-06-30 | 2020-12-19 | Project-In-progress | Release to RNY Customers | Completed
Account Center | A web-based application allowing customers to manage accounts, get information and perform other tasks related to NYPA services and products. | 2020-12-15 | 2023-06-30 | 2020-12-19 | Project-In-progress | Release to WNY Customers | Completed
Account Center | A web-based application allowing customers to manage accounts, get information and perform other tasks related to NYPA services and products. | 2020-12-15 | 2023-06-30 | 2021-08-21 | Project-In-progress | Release to Energy Services Customers | Future
Account Center | A web-based application allowing customers to manage accounts, get information and perform other tasks related to NYPA services and products. | 2020-12-15 | 2023-06-30 | 2021-08-22 | Project-In-progress | Release to StreetlightingCustomers | Future
Account Center | A web-based application allowing customers to manage accounts, get information and perform other tasks related to NYPA services and products. | 2020-12-15 | 2023-06-30 | 2021-08-23 | Project-In-progress | Release to Energy Services Customers | Future
Account Center | A web-based application allowing customers to manage accounts, get information and perform other tasks related to NYPA services and products. | 2020-12-15 | 2023-06-30 | 2021-08-24 | Project-In-progress | Release to StreetlightingCustomers | Future
Online Bill Pay | Provide customers the ability to setup, manage, and make online payments for power contracts, energy. | 2020-12-16 | 2022-06-30 | 2020-12-19 | Project-In-progress | Research And Requirements | Completed
Online Bill Pay | Provide customers the ability to setup, manage, and make online payments for power contracts, energy. | 2020-12-16 | 2022-06-30 | 2020-12-19 | Project-In-progress | Requirements review. | Completed
Online Bill Pay | Provide customers the ability to setup, manage, and make online payments for power contracts, energy. | 2020-12-16 | 2022-06-30 | 2021-08-24 | Project-In-progress | production release | Future
Online Bill Pay | Provide customers the ability to setup, manage, and make online payments for power contracts, energy. | 2020-12-16 | 2022-06-30 | 2021-08-25 | Project-In-progress | patch in progress | Future
Online Bill Pay | Provide customers the ability to setup, manage, and make online payments for power contracts, energy. | 2020-12-16 | 2022-06-30 | 2022-06-30 | Project-In-progress | regression defects delivery | Future
Online Bill Pay | Provide customers the ability to setup, manage, and make online payments for power contracts, energy. | 2020-12-16 | 2022-06-30 | 2021-08-27 | Project-In-progress | delivery to merchant | Future
Virtual Audits (NYEM) | Virtual Audits will provide integral benchmarking data, enabling customers to decide where to focus their efforts in an efficient and effective manner. | 2019-09-20 | 2020-10-25 | 2019-10-20 | Completed | Project kick-off | Completed
Virtual Audits (NYEM) | Virtual Audits will provide integral benchmarking data, enabling customers to decide where to focus their efforts in an efficient and effective manner. | 2019-09-20 | 2020-10-25 | 2019-11-21 | Completed | Requirements review. | Completed
Virtual Audits (NYEM) | Virtual Audits will provide integral benchmarking data, enabling customers to decide where to focus their efforts in an efficient and effective manner. | 2019-09-20 | 2020-10-25 | 2019-12-22 | Completed | Phase 1 approval. | Completed
Virtual Audits (NYEM) | Virtual Audits will provide integral benchmarking data, enabling customers to decide where to focus their efforts in an efficient and effective manner. | 2019-09-20 | 2020-10-25 | 2020-08-23 | Completed | Phase 1 complete. | Completed
Virtual Audits (NYEM) | Virtual Audits will provide integral benchmarking data, enabling customers to decide where to focus their efforts in an efficient and effective manner. | 2019-09-20 | 2020-10-25 | 2020-08-24 | Completed | Documents finalized. | Completed
Virtual Audits (NYEM) | Virtual Audits will provide integral benchmarking data, enabling customers to decide where to focus their efforts in an efficient and effective manner. | 2019-09-20 | 2020-10-25 | 2020-08-25 | Completed | Project complete | Completed